Smart Workspace Manager

Complete Work Plan - Project Start to End of Phase 2

| Version | 1.0 |
| --- | --- |
| Date | 18 June 2026 |
| Environment | Python 3.12, venv, pip |
| Cloud strategy | Azure free-first for personal use and testing |

Phase 1: 14 calendar days.

Phase 2: 6 active build days plus 1 contingency/finalization day.

Total planned duration: 21 calendar days.

Prepared as an independent Python learning project.

# Contents

1. Work Plan Purpose and Assumptions

2. Definition of Done

3. Overall Timeline

4. Phase 1 Work Plan - Days 1 to 14

5. Phase 1 Gate Review

6. Phase 2 Work Plan - Days 15 to 21

7. Phase 2 Gate Review

8. Daily Learning and Git Routine

9. Testing Strategy by Milestone

10. Azure Deployment Checklist

11. Deliverables Matrix

12. Contingency and Scope-Control Plan

13. Final Demonstration Script

# 1. Work Plan Purpose and Assumptions

This work plan covers the complete development path from an empty project directory to the end of Phase 2. The plan assumes that programming concepts are already familiar through Java, but Python syntax, libraries, tooling, and Python web/data practices are being learned during implementation.

| Item | Assumption |
| --- | --- |
| Duration | 21 calendar days: 14 days for Phase 1 and up to 7 days for Phase 2. |
| Daily effort | Flexible; a focused multi-hour development session is recommended. |
| Language/environment | Python 3.12, venv, pip, PowerShell, VS Code, Git, and GitHub. |
| Phase 1 | Streamlit + SQLite + reusable Python services. |
| Phase 2 | FastAPI + React/Vite + Azure SQL. |
| Cloud | Azure free plans for personal testing. |
| Not required | Conda, Docker, Kubernetes, paid Azure plans, background queues, or advanced ML. |

Schedule philosophy: Every day must end with a runnable state or a clearly isolated branch. Features are accepted only after a small test and a Git commit. Optional features are not allowed to delay the phase gate.

# 2. Definition of Done

## 2.1 Feature Definition of Done

The feature works through the active UI.

The core logic is located in backend/services/ or another correct backend layer.

Expected and invalid inputs are handled.

At least one automated test covers the reusable logic where practical.

Configuration values are not hard-coded.

README or relevant documentation is updated.

A meaningful Git commit records the completed feature.

## 2.2 Phase Definition of Done

All mandatory completion criteria pass.

A clean venv can install dependencies and run the system.

The cloud deployment passes a smoke test.

Known limitations are documented.

Optional unfinished work is moved to a future backlog, not left half-connected.

# 3. Overall Timeline

| Period | Focus | Main outcome |
| --- | --- | --- |
| Days 1-3 | Foundation | Environment, structure, Python refresh, settings, logging, storage and database foundations. |
| Days 4-7 | File management | Upload, validation, organization, metadata CRUD, and dashboard/library. |
| Days 8-11 | Data capabilities | CSV analysis, cleaning, charts, reports, and ML demonstration. |
| Days 12-14 | Quality and Phase 1 release | Tests, refactor, docs, Azure Streamlit deployment, and gate review. |
| Days 15-17 | Phase 2 backend and database | FastAPI, schemas/routes, Azure SQL, migrations, and auth basics. |
| Days 18-20 | React and cloud integration | React UI, API integration, deployment, and parity testing. |
| Day 21 | Buffer/finalization | Fix remaining defects, finalize documents, tag Phase 2, and run demonstration. |

# 4. Phase 1 Work Plan - Days 1 to 14

## Day 1 - Environment and repository

Confirm Python 3.12 through the launcher.

Activate the existing smart-workspace venv.

Initialize Git and GitHub repository.

Create the Phase 1 folder structure.

Create .gitignore, .env.example, requirements files, and a minimal README.

Install the initial packages and run a one-page Streamlit smoke test.

| Daily output | A clean repository that starts through Streamlit. |
| --- | --- |
| Learning focus | venv, pip, imports, packages, modules, Git basics. |

## Day 2 - Python syntax refresh and configuration

Implement backend/config/settings.py.

Practice Python data types, collections, conditions, loops, functions, comprehensions, and exceptions while creating validators and constants.

Create pathlib-based project path resolution.

Configure logging.

Add tests for simple validators and path helpers.

| Daily output | Configuration, validation, and logging foundations. |
| --- | --- |
| Learning focus | Python syntax differences from Java, pathlib, functions, exceptions, type hints. |

## Day 3 - Database and storage foundations

Create SQLAlchemy engine/session configuration for SQLite.

Define initial ORM models for files, reports, analysis jobs, logs, settings, and ML models.

Create repository functions for file CRUD.

Create storage_service with local and Azure-path-compatible roots.

Create a database initialization script and tests.

| Daily output | SQLite database and reusable local storage abstraction. |
| --- | --- |
| Learning focus | Classes, ORM models, context-managed sessions, CRUD, configuration. |

## Day 4 - File upload service

Implement safe file-name generation.

Validate file extension and size.

Save uploaded bytes through storage_service.

Create metadata record and return a structured result.

Handle duplicate names and partial failures.

Add file-service unit and integration tests.

| Daily output | Reliable upload workflow independent from Streamlit. |
| --- | --- |
| Learning focus | Binary files, pathlib, exceptions, dataclasses/objects, transactions. |

## Day 5 - Streamlit upload page

Build the upload page and call file_service.

Display success, validation, and error states.

Show original/stored name, type, size, and location.

Add upload limits to settings.

Test several valid and invalid file types manually.

| Daily output | Working browser-based file upload. |
| --- | --- |
| Learning focus | Streamlit widgets/state, UI-service separation, user feedback. |

## Day 6 - File organizer and automation logs

Implement category detection and destination rules.

Move or copy uploaded files safely into managed categories.

Update database metadata after movement.

Record automation logs.

Add organizer tests for categories, duplicate destinations, and failures.

| Daily output | Automatic organization with traceable logs. |
| --- | --- |
| Learning focus | Conditions, dictionaries, loops, file movement, custom exceptions, logging. |

## Day 7 - File library and dashboard

Build repository filters and dashboard summary queries.

Create file-library page with search, type filter, download, and delete.

Create dashboard cards and recent activity.

Ensure deletion handles both storage and database records.

Complete a Week 1 regression test and refactor duplicated code.

| Daily output | Complete file-management module. |
| --- | --- |
| Learning focus | Querying, filtering, aggregation, reusable UI components, integration testing. |

## Day 8 - CSV analysis service

Load a selected CSV with safe limits.

Return preview, shape, columns, data types, missing-value counts, duplicate count, and descriptive statistics.

Handle encoding/parsing failures.

Create structured analysis result objects.

Write tests using small sample CSV files.

| Daily output | Reusable pandas analysis service. |
| --- | --- |
| Learning focus | DataFrames, data types, exceptions, transformations, structured returns. |

## Day 9 - CSV analyzer page

Create file selection and analyzer controls.

Display preview and summary tables.

Display missing values and duplicates.

Allow column selection and basic filters.

Save an analysis job record and status.

| Daily output | Interactive data-analysis screen. |
| --- | --- |
| Learning focus | Streamlit data display, pandas integration, database workflow status. |

## Day 10 - Data cleaning and export

Implement duplicate removal.

Implement limited missing-value actions: drop rows, fill numeric values, fill text values.

Keep the original file unchanged.

Save the cleaned copy under processed/csv.

Export CSV and Excel.

Add cleaning tests.

| Daily output | Controlled cleaning pipeline with downloadable outputs. |
| --- | --- |
| Learning focus | Copy vs mutation, functions, DataFrame operations, openpyxl, file output. |

## Day 11 - Charts and reports

Create chart-selection logic based on column types.

Implement at least bar, histogram, line, and scatter options where valid.

Implement report_service for summary CSV/Excel/text or HTML reports.

Save report metadata.

Build the Reports page and report tests.

| Daily output | Visual analysis and report generation. |
| --- | --- |
| Learning focus | Plotting, reusable functions, formatting, file generation, metadata. |

## Day 12 - Basic ML lab

Use one small sample dataset with a clear target.

Implement preprocessing suitable for the selected data.

Split train/test data, train one simple model, calculate metrics, save with joblib, and predict one sample.

Build the ML Demo page.

Document that this is a learning feature, not an automated model for arbitrary datasets.

| Daily output | One complete lightweight ML workflow. |
| --- | --- |
| Learning focus | scikit-learn pipeline, model lifecycle, metrics, persistence, limitations. |

## Day 13 - Testing, refactor, and release preparation

Run all tests and add missing edge cases.

Refactor Streamlit pages so they only call services.

Add database/storage integration tests.

Review logging and error messages.

Freeze dependencies from the working environment.

Complete README local setup and usage instructions.

| Daily output | Stable Phase 1 release candidate. |
| --- | --- |
| Learning focus | pytest fixtures, test isolation, refactoring, dependency management. |

## Day 14 - Azure Phase 1 deployment and gate

Create one Azure resource group.

Create an App Service F1 Linux web app using a supported Python runtime.

Configure the Streamlit startup command and App Service settings.

Use /home/data as the cloud data root.

Deploy through GitHub or Deployment Center.

Run the smoke test: open, upload, analyze, report, and restart check.

Capture screenshots, document F1 limits, tag the release as phase-1.

| Daily output | Phase 1 deployed and formally accepted. |
| --- | --- |
| Learning focus | Azure App Service, startup commands, environment variables, logs, quotas. |

# 5. Phase 1 Gate Review

| Gate item | Pass condition |
| --- | --- |
| Local run | A clean venv installation starts Streamlit. |
| Files | Upload, organize, list, filter, download, and delete pass. |
| Data | Analyze and clean a CSV without changing the original. |
| Charts | At least three valid chart types display. |
| Reports | At least one downloadable report format works. |
| ML | The documented sample workflow trains, evaluates, saves, and predicts. |
| Architecture | No major business logic remains inside Streamlit pages. |
| Tests | Mandatory test suite passes. |
| Azure | F1 deployment passes the smoke test. |
| Documentation | README, screenshots, limitations, and setup instructions are complete. |

Stop/go rule: Do not start React until this gate passes. Fix architecture and service reuse first.

# 6. Phase 2 Work Plan - Days 15 to 21

The target is to complete the active build in six days. Day 21 is reserved for unresolved integration issues, documentation, and the final release. If Days 15-20 finish cleanly, Phase 2 is effectively completed in six days.

## Day 15 - FastAPI foundation

Create backend/main.py.

Add health route, CORS configuration, central exception handling, and dependency structure.

Create initial Pydantic schemas.

Wrap existing services with file and dashboard routes.

Run FastAPI locally with uvicorn.

Add health and file API tests.

| Daily output | Running FastAPI API that reuses Phase 1 services. |
| --- | --- |
| Learning focus | ASGI, routes, request/response models, decorators, status codes, dependency injection. |

## Day 16 - Complete API surface

Add analysis, cleaning, reports, ML, and settings endpoints.

Use consistent error response structures.

Add file-download responses safely.

Generate or review OpenAPI documentation.

Add API tests for valid, invalid, missing, and failure cases.

| Daily output | API parity for the main Phase 1 features. |
| --- | --- |
| Learning focus | REST design, HTTP methods, JSON, streaming/download responses, validation. |

## Day 17 - Azure SQL, migrations, and authentication

Create Azure SQL Database using the documented free offer.

Configure SQLAlchemy for SQLite locally and Azure SQL in cloud.

Initialize Alembic and create the first migration.

Add users and ownership fields.

Implement password hashing, login, token validation, and protected dependencies.

Test local and Azure database connections.

Set the free-limit behavior to avoid billable continuation.

| Daily output | Cloud database and personal authentication working. |
| --- | --- |
| Learning focus | Database URLs, migrations, relationships, secure hashing, JWT/session concepts. |

## Day 18 - React/Vite frontend foundation

Create the Vite React app inside frontend/.

Add router, layout, navigation, API client, environment config, loading states, and error states.

Build Login, Dashboard, File Upload, and File Library pages.

Connect to the local FastAPI backend.

| Daily output | React app performing login and file-management API calls. |
| --- | --- |
| Learning focus | Components, props/state, hooks, routing, axios/fetch, CORS. |

## Day 19 - React data features

Build CSV Analyzer, Cleaning, Reports, and ML pages.

Render returned tables and charts.

Implement report/file downloads.

Handle validation messages and token expiry.

Run feature-parity checks against the Streamlit app.

| Daily output | React covers all mandatory user workflows. |
| --- | --- |
| Learning focus | Frontend data flow, forms, conditional rendering, API contracts, chart integration. |

## Day 20 - Free Azure Phase 2 deployment

Build and deploy React to Azure Static Web Apps Free.

Repurpose the Phase 1 App Service F1 from Streamlit to FastAPI.

Configure the FastAPI startup command, Azure SQL URL, secrets, CORS frontend URL, and /home/data root.

Run cloud database migrations.

Execute full cloud smoke tests.

Create or confirm GitHub deployment workflows.

| Daily output | React, FastAPI, and Azure SQL operating together on free Azure services. |
| --- | --- |
| Learning focus | Separated deployment, cloud environment variables, CORS, migration execution, logs. |

## Day 21 - Contingency, legacy move, and final release

Fix remaining defects and repeat smoke tests.

Move Streamlit files to frontend/legacy_streamlit/ after React parity is confirmed.

Move Streamlit dependency to requirements-streamlit.txt.

Update README, API docs, Azure deployment notes, architecture screenshots, and known limitations.

Run a clean local setup and final test suite.

Tag the release as phase-2 and prepare the final demonstration.

| Daily output | Completed and documented Phase 2 release. |
| --- | --- |
| Learning focus | Release management, backward reference preservation, documentation, final QA. |

# 7. Phase 2 Gate Review

| Gate item | Pass condition |
| --- | --- |
| React | The active frontend is hosted on Static Web Apps Free. |
| FastAPI | All mandatory workflows use documented API endpoints. |
| Reuse | Routes call existing service functions rather than copied logic. |
| Database | The deployed app reads and writes Azure SQL through migrations/models. |
| Authentication | The personal user can log in and protected requests reject unauthenticated access. |
| Files | Upload, list, download, and delete work in cloud testing. |
| Analysis | CSV analysis, cleaning, charts, reports, and ML demo work through React. |
| Testing | Unit, integration, and API suites pass. |
| Legacy | Streamlit remains under legacy_streamlit/ and can be run with its separate requirements. |
| Cost | Resources use the intended free offers and budget/quota checks are documented. |
| Documentation | README, API, Azure, project, folder, and work-plan documents match the final system. |

# 8. Daily Learning and Git Routine

| Step | Daily practice |
| --- | --- |
| Start | Pull/confirm branch, activate venv, run tests, and read the day's target. |
| Learn | Study only the Python syntax/library concepts required for the task. |
| Implement | Write the smallest reusable backend function first, then connect the UI. |
| Test | Run the relevant unit/integration tests and one manual happy-path test. |
| Refactor | Remove duplication, improve names/types, and confirm layer boundaries. |
| Document | Update README notes, environment variables, and known limitations. |
| Commit | Create one or more meaningful commits; avoid one giant end-of-day commit. |
| End | Run the application from the normal entry point and record the next task. |

# 9. Testing Strategy by Milestone

| Checkpoint | Required test focus |
| --- | --- |
| After Day 3 | Settings, validators, database initialization, and repository CRUD. |
| After Day 6 | Upload, safe names, categories, movement, rollback/failure, and logs. |
| After Day 8 | CSV parsing, limits, missing values, duplicates, and statistics. |
| After Day 11 | Cleaning outputs, chart preparation, reports, and metadata. |
| After Day 12 | ML preprocessing, training, metrics, persistence, and prediction. |
| After Day 14 | Full Phase 1 regression and Azure smoke test. |
| After Day 16 | API success/validation/not-found/error tests. |
| After Day 17 | Auth, Azure SQL connection, migration, and ownership tests. |
| After Day 19 | React/API parity manual test. |
| After Day 20 | Cloud end-to-end smoke test. |
| Day 21 | Fresh setup, full test suite, and release acceptance. |

# 10. Azure Deployment Checklist

## 10.1 Phase 1 App Service F1

Resource group created.

Linux App Service F1 selected.

Python runtime compatible with project dependencies selected.

requirements.txt detected and installed.

Streamlit startup command configured.

DATA_ROOT=/home/data configured.

SECRET_KEY and environment variables configured in App Service settings.

Log stream checked.

Upload, analysis, report, and restart smoke tests passed.

F1 quotas and no-production-SLA limitation documented.

## 10.2 Phase 2 Static Web Apps + FastAPI + Azure SQL

React repository/build settings correct for frontend/.

Static Web Apps Free selected.

Frontend API base URL configured.

App Service repurposed with FastAPI startup command.

CORS allows only the local and deployed frontend origins.

Azure SQL free offer selected and free-limit behavior configured safely.

DATABASE_URL, auth secrets, and environment settings configured.

Migrations executed.

Health, login, upload, analysis, report, and delete smoke tests passed.

Azure Cost Management/budget alerts checked.

# 11. Deliverables Matrix

| Deliverable group | Target days | Evidence |
| --- | --- | --- |
| Project setup | D1-D3 | Repository, venv, folders, settings, logging, database. |
| File management | D4-D7 | Upload, organizer, library, dashboard, metadata, tests. |
| Data analysis | D8-D10 | Analyzer, cleaning, exports, sample data tests. |
| Visualization/reporting | D11 | Charts, reports, report history. |
| ML | D12 | One documented basic ML workflow. |
| Phase 1 release | D13-D14 | Tests, README, Azure Streamlit deployment, tag. |
| FastAPI | D15-D16 | API, schemas, docs, tests. |
| Database/auth | D17 | Azure SQL, Alembic, login/protected routes. |
| React | D18-D19 | Active professional frontend with parity. |
| Phase 2 cloud | D20 | Static Web Apps + App Service + Azure SQL. |
| Final release | D21 | Legacy move, full docs, QA, tag, demo. |

# 12. Contingency and Scope-Control Plan

| Priority | Scope |
| --- | --- |
| Mandatory | Upload, organize, metadata, library, CSV summary, basic cleaning, reports, tests, Streamlit deployment, FastAPI, React, Azure SQL, authentication basics. |
| Should have | Multiple charts, Excel export, ML persistence, GitHub deployment automation. |
| Optional | PDF report, advanced cleaning UI, complex model selection, roles, password reset, background jobs, Blob Storage, Docker. |
| Remove first when delayed | PDF, extra chart types, arbitrary-dataset ML, frontend animations, advanced settings, CI/CD polish. |
| Never compromise | Service separation, safe file handling, secrets, database correctness, core tests, and documentation accuracy. |

Phase 2 under seven days: The schedule is achievable only because Phase 2 reuses a tested backend service layer and implements React parity rather than adding a second set of new product features.

# 13. Final Demonstration Script

Open the deployed React application and log in.

Show the dashboard and explain that React calls FastAPI.

Upload a small CSV and show its stored metadata.

Open the file library and demonstrate filtering.

Analyze the CSV and show preview, data types, missing values, duplicates, and summary statistics.

Apply one cleaning operation and download the cleaned file.

Generate and download a report.

Run the small ML demonstration and show metrics/prediction.

Open the FastAPI documentation and show one endpoint contract.

Show the Azure architecture: Static Web Apps Free, App Service F1, and Azure SQL free offer.

Show the repository structure and explain service reuse and legacy_streamlit/.

Show the passing test result and state the free-tier limitations and future publication upgrade path.