Smart Workspace Manager

Complete Work Plan - Updated with SQL, Auth, Authorization, Azure SQL, GitHub Actions, and React DOM Basics

| Version | 2.0 |
| --- | --- |
| Updated | 26 July 2026 |
| Environment | Python 3.12, venv, pip |
| Cloud strategy | Azure free-first for personal use and testing |

Phase 1: 14 calendar days.

Phase 2: 6 active build days plus 1 contingency/finalization day.

Total planned duration: 21 calendar days.

Prepared as an independent Python learning project.

# Contents

1. Work Plan Purpose and Assumptions

2. Definition of Done

3. Overall Timeline

4. Phase 1 Work Plan - Days 1 to 14

5. Phase 1 Gate Review

6. Phase 2 Work Plan - Days 15 to 21

7. Phase 2 Gate Review

8. Daily Learning and Git Routine

9. Testing Strategy by Milestone

10. Azure Deployment and CI/CD Checklist

11. Deliverables Matrix

12. Contingency and Scope-Control Plan

13. Final Demonstration Script

# 1. Work Plan Purpose and Assumptions

This work plan covers the complete development path from an empty project directory to the end of Phase 2. It now explicitly includes raw SQL querying, SQLAlchemy implementation, authentication, ownership-based authorization, Azure SQL Database creation, GitHub Actions CI/CD, and basic DOM/browser concepts through React.

| Item | Assumption |
| --- | --- |
| Duration | 21 calendar days: 14 days for Phase 1 and up to 7 days for Phase 2. |
| Daily effort | Flexible; a focused multi-hour development session is recommended. |
| Language/environment | Python 3.12, venv, pip, PowerShell, VS Code, Git, and GitHub. |
| Phase 1 | Streamlit + SQLite + reusable Python services + raw SQL practice. |
| Phase 2 | FastAPI + React/Vite + Azure SQL + authentication + authorization + GitHub Actions. |
| Cloud | Azure free plans for personal testing, subject to subscription eligibility. |
| Not required | Conda, Docker, Kubernetes, paid Azure plans, background queues, advanced ML, or advanced vanilla DOM work. |

Schedule philosophy: Every day must end with a runnable state or a clearly isolated branch. Features are accepted only after a small test and a Git commit. Optional features are not allowed to delay the phase gate.

# 2. Definition of Done

## 2.1 Feature Definition of Done

The feature works through the active UI or API.

The core logic is located in backend/services/ or another correct backend layer.

Expected and invalid inputs are handled.

For database features, the raw SQL idea is understood before the SQLAlchemy implementation.

For protected features, authentication and ownership behavior are tested.

At least one automated test covers the reusable logic where practical.

Configuration values and secrets are not hard-coded.

README or relevant documentation is updated.

A meaningful Git commit records the completed feature.

## 2.2 Phase Definition of Done

All mandatory completion criteria pass.

A clean venv can install dependencies and run the system.

The cloud deployment passes a smoke test.

Known limitations are documented.

Optional unfinished work is moved to a future backlog, not left half-connected.

# 3. Overall Timeline

| Period | Focus | Main outcome |
| --- | --- | --- |
| Days 1-3 | Foundation | Environment, structure, Python refresh, settings, logging, raw SQL basics, SQLite, storage, and database foundations. |
| Days 4-7 | File management | Upload, validation, organization, metadata CRUD, raw SQL filters/aggregates, and dashboard/library. |
| Days 8-11 | Data capabilities | CSV analysis, cleaning, charts, reports, and ML demonstration. |
| Days 12-14 | Quality and Phase 1 release | Tests, refactor, docs, Azure Streamlit deployment, and gate review. |
| Days 15-17 | Phase 2 backend, database, and auth | FastAPI, schemas/routes, Azure SQL, migrations, authentication, and authorization. |
| Days 18-20 | React, DOM basics, cloud, and CI/CD | React UI, DOM/browser concepts, API integration, GitHub Actions, deployment, and parity testing. |
| Day 21 | Buffer/finalization | Fix defects, finalize documents, verify workflows, tag Phase 2, and run demonstration. |

# 4. Phase 1 Work Plan - Days 1 to 14

## Day 1 - Environment and repository

Confirm Python 3.12 through the launcher.

Activate the existing smart-workspace venv.

Initialize Git and GitHub repository.

Create the Phase 1 folder structure.

Create .gitignore, .env.example, requirements files, and a minimal README.

Install the initial packages and run a one-page Streamlit smoke test.

| Daily output | A clean repository that starts through Streamlit. |
| --- | --- |
| Learning focus | venv, pip, imports, packages, modules, Git basics. |

## Day 2 - Python syntax refresh and configuration

Implement backend/config/settings.py.

Practice Python data types, collections, conditions, loops, functions, comprehensions, and exceptions while creating validators and constants.

Create pathlib-based project path resolution.

Configure logging.

Add tests for simple validators and path helpers.

| Daily output | Configuration, validation, and logging foundations. |
| --- | --- |
| Learning focus | Python syntax differences from Java, pathlib, functions, exceptions, type hints. |

## Day 3 - Database and storage foundations

Write raw SQL CREATE TABLE examples before creating SQLAlchemy models.

Write raw SQL INSERT, SELECT, UPDATE, and DELETE examples for the files table.

Create SQLAlchemy engine/session configuration for SQLite.

Define initial ORM models for files, reports, analysis jobs, logs, settings, and ML models.

Create repository functions for file CRUD using SQLAlchemy.

Compare raw SQL output with SQLAlchemy repository output.

Create storage_service with local and Azure-path-compatible roots.

Create a database initialization script and tests.

Document the raw SQL query and its SQLAlchemy equivalent.

| Daily output | SQLite database, raw SQL examples, SQLAlchemy repositories, and reusable local storage abstraction. |
| --- | --- |
| Learning focus | SQL basics, SQLite, SQLAlchemy models, sessions, CRUD, raw SQL vs ORM, configuration. |

## Day 4 - File upload service

Implement safe file-name generation.

Validate file extension and size.

Save uploaded bytes through storage_service.

Create metadata record and return a structured result.

Handle duplicate names and partial failures.

Add file-service unit and integration tests.

| Daily output | Reliable upload workflow independent from Streamlit. |
| --- | --- |
| Learning focus | Binary files, pathlib, exceptions, dataclasses/objects, transactions. |

## Day 5 - Streamlit upload page

Build the upload page and call file_service.

Display success, validation, and error states.

Show original/stored name, type, size, and location.

Add upload limits to settings.

Test several valid and invalid file types manually.

| Daily output | Working browser-based file upload. |
| --- | --- |
| Learning focus | Streamlit widgets/state, UI-service separation, user feedback. |

## Day 6 - File organizer and automation logs

Implement category detection and destination rules.

Move or copy uploaded files safely into managed categories.

Update database metadata after movement.

Record automation logs.

Add organizer tests for categories, duplicate destinations, and failures.

| Daily output | Automatic organization with traceable logs. |
| --- | --- |
| Learning focus | Conditions, dictionaries, loops, file movement, custom exceptions, logging. |

## Day 7 - File library and dashboard

Write raw SQL queries for file list, search, filter, count, and group-by-file-type dashboard summaries.

Build repository filters and dashboard summary queries using SQLAlchemy.

Compare raw SQL output with SQLAlchemy output.

Create file-library page with search, type filter, download, and delete.

Create dashboard cards and recent activity.

Ensure deletion handles both storage and database records.

Complete a Week 1 regression test and refactor duplicated code.

| Daily output | Complete file-management module with SQL query understanding. |
| --- | --- |
| Learning focus | SELECT, WHERE, LIKE, ORDER BY, COUNT, GROUP BY, SQLAlchemy filtering and aggregation, reusable UI components. |

## Day 8 - CSV analysis service

Load a selected CSV with safe limits.

Return preview, shape, columns, data types, missing-value counts, duplicate count, and descriptive statistics.

Handle encoding/parsing failures.

Create structured analysis result objects.

Write tests using small sample CSV files.

| Daily output | Reusable pandas analysis service. |
| --- | --- |
| Learning focus | DataFrames, data types, exceptions, transformations, structured returns. |

## Day 9 - CSV analyzer page

Create file selection and analyzer controls.

Display preview and summary tables.

Display missing values and duplicates.

Allow column selection and basic filters.

Save an analysis job record and status.

| Daily output | Interactive data-analysis screen. |
| --- | --- |
| Learning focus | Streamlit data display, pandas integration, database workflow status. |

## Day 10 - Data cleaning and export

Implement duplicate removal.

Implement limited missing-value actions: drop rows, fill numeric values, fill text values.

Keep the original file unchanged.

Save the cleaned copy under processed/csv.

Export CSV and Excel.

Add cleaning tests.

| Daily output | Controlled cleaning pipeline with downloadable outputs. |
| --- | --- |
| Learning focus | Copy vs mutation, functions, DataFrame operations, openpyxl, file output. |

## Day 11 - Charts and reports

Create chart-selection logic based on column types.

Implement at least bar, histogram, line, and scatter options where valid.

Implement report_service for summary CSV/Excel/text or HTML reports.

Save report metadata.

Build the Reports page and report tests.

| Daily output | Visual analysis and report generation. |
| --- | --- |
| Learning focus | Plotting, reusable functions, formatting, file generation, metadata. |

## Day 12 - Basic ML lab

Use one small sample dataset with a clear target.

Implement preprocessing suitable for the selected data.

Split train/test data, train one simple model, calculate metrics, save with joblib, and predict one sample.

Build the ML Demo page.

Document that this is a learning feature, not an automated model for arbitrary datasets.

| Daily output | One complete lightweight ML workflow. |
| --- | --- |
| Learning focus | scikit-learn pipeline, model lifecycle, metrics, persistence, limitations. |

## Day 13 - Testing, refactor, and release preparation

Run all tests and add missing edge cases.

Refactor Streamlit pages so they only call services.

Add database/storage integration tests.

Confirm raw SQL examples and SQLAlchemy equivalents are documented.

Review logging and error messages.

Freeze dependencies from the working environment.

Complete README local setup and usage instructions.

| Daily output | Stable Phase 1 release candidate. |
| --- | --- |
| Learning focus | pytest fixtures, test isolation, refactoring, dependency management, database documentation. |

## Day 14 - Azure Phase 1 deployment and gate

Create one Azure resource group.

Create an App Service F1 Linux web app using a supported Python runtime.

Configure the Streamlit startup command and App Service settings.

Use /home/data as the cloud data root.

Deploy through GitHub or Deployment Center.

Run the smoke test: open, upload, analyze, report, and restart check.

Capture screenshots, document F1 limits, tag the release as phase-1.

| Daily output | Phase 1 deployed and formally accepted. |
| --- | --- |
| Learning focus | Azure App Service, startup commands, environment variables, logs, quotas. |

# 5. Phase 1 Gate Review

| Gate item | Pass condition |
| --- | --- |
| Local run | A clean venv installation starts Streamlit. |
| Files | Upload, organize, list, filter, download, and delete pass. |
| SQL | Raw SQL and SQLAlchemy equivalents exist for main file/database operations. |
| Data | Analyze and clean a CSV without changing the original. |
| Charts | At least three valid chart types display. |
| Reports | At least one downloadable report format works. |
| ML | The documented sample workflow trains, evaluates, saves, and predicts. |
| Architecture | No major business logic remains inside Streamlit pages. |
| Tests | Mandatory test suite passes. |
| Azure | F1 deployment passes the smoke test. |
| Documentation | README, screenshots, SQL notes, limitations, and setup instructions are complete. |

Stop/go rule: Do not start React until this gate passes. Fix architecture, SQL clarity, and service reuse first.

# 6. Phase 2 Work Plan - Days 15 to 21

The target is to complete the active build in six days. Day 21 is reserved for unresolved integration issues, documentation, workflow verification, and the final release.

## Day 15 - FastAPI foundation

Create backend/main.py.

Add health route, CORS configuration, central exception handling, and dependency structure.

Create initial Pydantic schemas.

Wrap existing services with file and dashboard routes.

Add protected-route structure even before full authentication is completed.

Add API response pattern for 401 Unauthorized and 403 Forbidden.

Run FastAPI locally with uvicorn.

Add health and file API tests.

| Daily output | Running FastAPI API that reuses Phase 1 services. |
| --- | --- |
| Learning focus | ASGI, routes, request/response models, decorators, status codes, protected route structure, dependency injection. |

## Day 16 - Complete API surface

Add analysis, cleaning, reports, ML, and settings endpoints.

Use consistent error response structures.

Add file-download responses safely.

Add ownership-aware API design to file, analysis, report, and ML endpoints.

Generate or review OpenAPI documentation.

Add API tests for valid, invalid, missing, unauthorized, forbidden, and failure cases.

| Daily output | API parity for the main Phase 1 features with authorization-aware design. |
| --- | --- |
| Learning focus | REST design, HTTP methods, JSON, streaming/download responses, validation, authorization-aware endpoints. |

## Day 17 - Azure SQL, migrations, authentication, and authorization

Create Azure SQL Database using the documented free offer if available in the subscription.

Configure firewall/network access and database connection string.

Configure SQLAlchemy for SQLite locally and Azure SQL in cloud.

Initialize Alembic and create the first migration.

Add users table and ownership fields such as user_id.

Write raw SQL JOIN and ownership-filter examples.

Implement password hashing.

Implement login and token/session creation.

Implement protected FastAPI dependencies.

Implement ownership-based authorization: user can access only their own files, analysis jobs, reports, and ML models.

Test local and Azure database connections.

Test login, invalid login, missing token, invalid token, and forbidden access.

Set the Azure SQL free-limit behavior to avoid billable continuation where available.

Document a fallback if the Azure SQL free offer is unavailable for the subscription.

| Daily output | Azure SQL, migrations, authentication, and basic ownership authorization working. |
| --- | --- |
| Learning focus | Azure SQL, raw SQL joins, SQLAlchemy relationships, Alembic migrations, password hashing, JWT/session logic, protected routes, 401 vs 403. |

## Day 18 - React/Vite frontend foundation

Create the Vite React app inside frontend/.

Add router, layout, navigation, API client, environment config, loading states, and error states.

Build Login, Dashboard, File Upload, and File Library pages.

Practice controlled inputs in login and upload forms.

Practice button click events and form submit events.

Practice conditional rendering for loading, success, validation error, and authentication states.

Use useRef once for a simple direct DOM-related task such as focusing an input or resetting a file input.

Connect to the local FastAPI backend.

| Daily output | React app performing login and file-management API calls while demonstrating basic DOM/browser concepts. |
| --- | --- |
| Learning focus | React components, props, state, events, controlled inputs, conditional rendering, useRef, API calls, CORS. |

## Day 19 - React data features

Build CSV Analyzer, Cleaning, Reports, and ML pages.

Render returned tables and charts.

Implement report/file downloads.

Handle validation messages and token expiry.

Add frontend handling for 401 Unauthorized and 403 Forbidden responses.

Show user-friendly authorization error messages.

Practice dynamic rendering of tables and charts from API responses.

Run feature-parity checks against the Streamlit app.

| Daily output | React covers all mandatory user workflows with auth-aware UI behavior. |
| --- | --- |
| Learning focus | Frontend data flow, auth-aware UI, conditional rendering, API error handling, dynamic UI rendering, chart integration. |

## Day 20 - Free Azure Phase 2 deployment and basic CI/CD

Create backend GitHub Actions workflow.

Backend workflow should install Python dependencies and run pytest.

Deploy FastAPI to Azure App Service F1 after tests pass.

Create frontend GitHub Actions workflow.

Frontend workflow should install Node dependencies and build React.

Deploy React to Azure Static Web Apps Free.

Store Azure publish credentials, Static Web Apps token, API URL, database URL, and secrets safely using GitHub Secrets/Azure app settings.

Configure FastAPI startup command, Azure SQL URL, secrets, CORS frontend URL, and /home/data root.

Run cloud database migrations.

Execute full cloud smoke tests.

| Daily output | React, FastAPI, Azure SQL, and basic GitHub Actions CI/CD working on free Azure services. |
| --- | --- |
| Learning focus | GitHub Actions, CI/CD basics, GitHub Secrets, Azure deployment, frontend build, backend tests, cloud environment variables. |

## Day 21 - Contingency, legacy move, and final release

Fix remaining defects and repeat smoke tests.

Confirm GitHub Actions workflows run successfully from a fresh push.

Move Streamlit files to frontend/legacy_streamlit/ after React parity is confirmed.

Move Streamlit dependency to requirements-streamlit.txt.

Document raw SQL examples and SQLAlchemy equivalents.

Document authentication and authorization behavior.

Document Azure SQL creation steps and any subscription limitations/fallbacks.

Document CI/CD workflow files and GitHub Secrets used.

Document React DOM/browser concepts practiced.

Update README, API docs, Azure deployment notes, architecture screenshots, and known limitations.

Run a clean local setup and final test suite.

Tag the release as phase-2 and prepare the final demonstration.

| Daily output | Completed and documented Phase 2 release. |
| --- | --- |
| Learning focus | Release management, GitHub Actions verification, backward reference preservation, documentation, final QA. |

# 7. Phase 2 Gate Review

| Gate item | Pass condition |
| --- | --- |
| React | The active frontend is hosted on Static Web Apps Free. |
| FastAPI | All mandatory workflows use documented API endpoints. |
| Reuse | Routes call existing service functions rather than copied logic. |
| SQL | Raw SQL examples and SQLAlchemy equivalents are documented. |
| Database | The deployed app reads and writes Azure SQL through migrations/models, or an eligibility fallback is documented. |
| Authentication | The personal user can log in and protected requests reject unauthenticated access. |
| Authorization | A user cannot access another user's files, reports, analyses, or models. |
| DOM/browser basics | React UI demonstrates controlled inputs, events, conditional rendering, dynamic rendering, and one useRef example. |
| CI/CD | Backend and frontend GitHub Actions workflows run successfully. |
| Files | Upload, list, download, and delete work in cloud testing. |
| Analysis | CSV analysis, cleaning, charts, reports, and ML demo work through React. |
| Testing | Unit, integration, API, auth, authorization, and CI checks pass. |
| Legacy | Streamlit remains under legacy_streamlit/ and can be run with its separate requirements. |
| Cost | Resources use intended free offers and budget/quota checks are documented. |
| Documentation | README, API, Azure, project, folder, CI/CD, SQL notes, and work-plan documents match the final system. |

# 8. Daily Learning and Git Routine

| Step | Daily practice |
| --- | --- |
| Start | Pull/confirm branch, activate venv, run tests, and read the day's target. |
| Learn | Study only the Python syntax/library concepts required for the task. |
| Implement | Write the smallest reusable backend function first, then connect the UI or API. |
| SQL step | For DB work, write or explain raw SQL first, then implement SQLAlchemy. |
| Security step | For protected work, add auth/authorization checks and tests. |
| Test | Run the relevant unit/integration/API tests and one manual happy-path test. |
| Refactor | Remove duplication, improve names/types, and confirm layer boundaries. |
| Document | Update README notes, environment variables, SQL notes, auth behavior, and known limitations. |
| Commit | Create one or more meaningful commits; avoid one giant end-of-day commit. |
| End | Run the application from the normal entry point and record the next task. |

# 9. Testing Strategy by Milestone

| Checkpoint | Required test focus |
| --- | --- |
| After Day 3 | Settings, validators, database initialization, raw SQL examples, SQLAlchemy repository CRUD. |
| After Day 6 | Upload, safe names, categories, movement, rollback/failure, and logs. |
| After Day 7 | File filters, dashboard aggregates, raw SQL vs SQLAlchemy output checks. |
| After Day 8 | CSV parsing, limits, missing values, duplicates, and statistics. |
| After Day 11 | Cleaning outputs, chart preparation, reports, and metadata. |
| After Day 12 | ML preprocessing, training, metrics, persistence, and prediction. |
| After Day 14 | Full Phase 1 regression and Azure smoke test. |
| After Day 16 | API success/validation/not-found/unauthorized/forbidden/error tests. |
| After Day 17 | Auth, Azure SQL connection, migration, ownership, raw SQL JOIN/ownership query tests. |
| After Day 19 | React/API parity, auth-aware UI, 401/403 handling, DOM/browser behavior manual test. |
| After Day 20 | GitHub Actions backend/frontend workflows and cloud end-to-end smoke test. |
| Day 21 | Fresh setup, full test suite, workflow verification, and release acceptance. |

# 10. Azure Deployment and CI/CD Checklist

## 10.1 Phase 1 App Service F1

Resource group created.

Linux App Service F1 selected.

Python runtime compatible with project dependencies selected.

requirements.txt detected and installed.

Streamlit startup command configured.

DATA_ROOT=/home/data configured.

SECRET_KEY and environment variables configured in App Service settings.

Log stream checked.

Upload, analysis, report, and restart smoke tests passed.

F1 quotas and no-production-SLA limitation documented.

## 10.2 Phase 2 Static Web Apps + FastAPI + Azure SQL + GitHub Actions

React repository/build settings correct for frontend/.

Static Web Apps Free selected.

Frontend API base URL configured.

App Service repurposed with FastAPI startup command.

CORS allows only the local and deployed frontend origins.

Azure SQL free offer selected if available; free-limit behavior configured safely.

DATABASE_URL, auth secrets, API URL, Azure publish credentials, and Static Web Apps token stored safely.

Backend GitHub Actions workflow installs Python dependencies and runs pytest.

Backend workflow deploys FastAPI to Azure App Service after tests pass.

Frontend GitHub Actions workflow installs Node dependencies and builds React.

Frontend workflow deploys React to Azure Static Web Apps.

Migrations executed.

Health, login, ownership/forbidden check, upload, analysis, report, and delete smoke tests passed.

Azure Cost Management/budget alerts checked.

# 11. Deliverables Matrix

| Deliverable group | Target days | Evidence |
| --- | --- | --- |
| Project setup | D1-D3 | Repository, venv, folders, settings, logging, raw SQL examples, SQLite database. |
| File management | D4-D7 | Upload, organizer, library, dashboard, metadata, raw SQL filters/aggregates, tests. |
| Data analysis | D8-D10 | Analyzer, cleaning, exports, sample data tests. |
| Visualization/reporting | D11 | Charts, reports, report history. |
| ML | D12 | One documented basic ML workflow. |
| Phase 1 release | D13-D14 | Tests, README, Azure Streamlit deployment, tag. |
| FastAPI | D15-D16 | API, schemas, docs, protected-route structure, tests. |
| Database/auth/authz | D17 | Azure SQL, Alembic, login/protected routes, ownership authorization. |
| React + DOM basics | D18-D19 | Active professional frontend with parity, controlled inputs, events, conditional rendering, useRef. |
| Phase 2 cloud + CI/CD | D20 | Static Web Apps + App Service + Azure SQL + GitHub Actions workflows. |
| Final release | D21 | Legacy move, SQL notes, auth/authz docs, CI/CD docs, QA, tag, demo. |

# 12. Contingency and Scope-Control Plan

| Priority | Scope |
| --- | --- |
| Mandatory | Upload, organize, metadata, library, raw SQL basics, SQLAlchemy repositories, CSV summary, basic cleaning, reports, tests, Streamlit deployment, FastAPI, React, Azure SQL attempt, authentication, ownership authorization, basic GitHub Actions. |
| Should have | Multiple charts, Excel export, ML persistence, frontend auth polish, automatic deployment from main branch. |
| Optional | PDF report, advanced cleaning UI, complex model selection, roles, password reset, background jobs, Blob Storage, Docker. |
| Remove first when delayed | PDF, extra chart types, arbitrary-dataset ML, frontend animations, advanced settings, advanced CI/CD polish. |
| Never compromise | Service separation, raw SQL understanding, safe file handling, secrets, database correctness, auth/authorization correctness, core tests, documentation accuracy. |

Phase 2 under seven days: The schedule is achievable only because Phase 2 reuses a tested backend service layer, keeps authorization ownership-based only, and implements basic GitHub Actions rather than advanced release engineering.

# 13. Final Demonstration Script

Open the deployed React application and log in.

Show that a protected route rejects unauthenticated access.

Show the dashboard and explain that React calls FastAPI.

Upload a small CSV and show its stored metadata.

Explain ownership-based authorization and show that file queries are user-scoped.

Show one raw SQL query and the equivalent SQLAlchemy repository code.

Open the file library and demonstrate filtering.

Analyze the CSV and show preview, data types, missing values, duplicates, and summary statistics.

Apply one cleaning operation and download the cleaned file.

Generate and download a report.

Run the small ML demonstration and show metrics/prediction.

Open the FastAPI documentation and show one endpoint contract.

Show Azure architecture: Static Web Apps Free, App Service F1, and Azure SQL or documented fallback.

Show Azure SQL Database in the Azure portal if the free offer was available.

Show the GitHub Actions workflow run for backend tests/deployment.

Show the GitHub Actions workflow run for frontend build/deployment.

Show one React form using controlled inputs, event handling, conditional rendering, and one simple useRef example.

Show the repository structure and explain service reuse and legacy_streamlit/.

Show the passing test result and state the free-tier limitations and future publication upgrade path.